Chapter 25: Project Execution, Monitoring and Control (FPM2ed p.316)

1. Project Execution, Monitoring and Control

2. Body of Knowledge Mapping

3. Project Planning and Control Cycle

4. Monitor Progress (Data Capture)

5. How to Apply Project Control

The following questions have been designed to test your knowledge of the chapter and prompt discussion. Please note that each question could have one or more correct answers.

25.1: Which one of the following lists the four Processes of the Project Management Process? (FPM2ed p.317)

a. Business Case, Execute, Control, Close.

b. Project Plan, Execute, Control, Close

c. Initiate, Plan, Execute, Close.

d. Initiate, Plan, Execute, Control.

25.1 Answer: C is correct. A, B, and D are incorrect.

25.2: Which one of the following relates to the Initiation Process? (FPM2ed p.317)

a. The initiation process takes the go no/go decision.

b. The initiation process includes the sunk cost charter.

c. The initiation process expedites the project’s progress.

d. The initiation process writes the project’s closeout report.

25.2 Answer: A is correct. B, C and D are incorrect.

25.3: Which one of the following Phases in the Project Life Cycle includes the Project Execution? (FPM2ed p.318)

a. The business case phase.

b. The feasibility study phase.

c. The project initiation phase.

d. The project execution phase.

25.3 Answer: D is correct. A, B and C are incorrect.

25.4: Which two of the following relate to Project Expediting? (FPM2ed p.319)

a. Project expediting confirms the contractors and suppliers have received the orders.

b. Project expediting confirms the level of sunk costs.

c. Project expediting follows up on the orders to ensure and encourage the suppliers to meet their contractual requirements.

d. Project expediting confirms the client has sufficient funds to pay for the project.

25.4 Answer: A and C are correct. B and D are incorrect.

25.5: Which two of the following relate to the Scope Change Process? (FPM2ed p.319)

a. The scope change process is approved by the project expeditor.

b. The scope change control process ensures that all changes to the scope of work are captured and approved by the designated people.

c. The scope change control process ensures the functionality of the configuration arrangement.

d. The scope change control process ensures there is sufficient scope creep.

25.5 Answer: B and C are correct. A and D are incorrect.

25.6: Which two of the following relate to the Project Control Cycle? (FPM2ed p.310)

a. The project control cycle authorizes the project’s work at the beginning of each cycle.

b. The project control cycle monitors the project’s progress.

c. The project control cycle develops the business case.

d. The project control cycle determines the sunk costs.

25.6 Answer: A and B are correct. C and D are incorrect.

25.7: Which one of the following relates to Overoptimistic Reporting? (FPM2ed p.322)

a. Overoptimistic reporting over reports the sunk costs.

b. Overoptimistic reporting over reports the planned value.

c. Overoptimistic reporting over reports the earned value.

d. Overoptimistic reporting over reports the actual costs.

25.7 Answer: C is correct. A, B and D are incorrect.

25.8: Which three of the following relate to Data Capture? (FPM2ed p.324)

a. The project manager sets up a data capture template.

b. As the size of the work packages are reduced so the accuracy of the data capture will increase.

c. The Gantt chart can be used to capture progress.

d. The progress report can be used to determine the level of sunk cost data capture.

25.8 Answer: A, B and C are correct. D is incorrect.

25.9: Which three of the following relate to How to Apply Project Control? (FPM2ed p.325)

a. Discuss changes with the foreman first.

b. An effective way to achieve commitment is to make the contractor aware of the cost of any delay to the project.

c. The project manager should encourage the team members to report on deviations and exceptions (management-by-exception) as a method of highlighting problem areas. The project manager can set the limits.

d. The project sponsor is responsible for applying project control at the project level.

25.9 Answer: A, B and C are correct. D is incorrect.

25.10: Which two of the following relate to the Reporting Frequency? (FPM2ed p.326)

a. The reporting frequency is best received on FM.

b. Short reporting periods are best when there is a high level of change and uncertainty in the project.

c. Long reporting periods are best when there is little or no change.

d. The reporting frequency is best received on AM.

25.10 Answer: B and C are correct. This is similar to the agile approach where the ‘sprint’ planning and control cycle is adjusted to suit the project. A and D are incorrect.