Chapter 27: Earned Value Management (FPM2ed p.335)

1. Earned Value Management

2. Body of Knowledge Mapping

3. Earned Value

4. Earned Value Exercise 2

5. Project Control

6. Earned Value Example

The following questions have been designed to test your knowledge of the chapter and prompt discussion. Please note that each question could have one or more correct answers.

27.1: Which three of the following relate to the Earned Value Method? (FPM2ed p.334)

a. The earned value method plans and controls the project in comparable units.

b. The earned value method integrates cost and time.

c. The earned value method integrates man-hours and time.

d. The earned value method integrates the business case and the project charter.

27.1 Answer: A, B and C are correct. D is incorrect.

27.2: Which one of the following is the Earned Value term for the Budget? (FPM2ed p.337)

a. EAC (estimate at completion).

b. BAC (budget at completion).

c. PV (planned value at completion).

d. WBS (work package at completion).

27.2 Answer: B is correct. The budget at completion is the cost estimate or quotation of the funds required to perform the original scope of work.  A, C and D are incorrect.

27.3: Which one of the following relates to the Earned Value term PV (Planned Value)? (FPM2ed p.337)

a. Planned value is the total value of the project at completion.

b. Planned value is the initial budget for the project at completion.

c. Planned value is the integration of cost and time to give the characteristic S curve which forms the baseline plan.

d. Planned value is the value earned by the project at completion.

27.3 Answer: C is correct. The PV can also be man-hours and time or any suitable parameter that flows evenly through the project. The key feature is the integration of the parameter and time. A, B and D are incorrect.

27.4: Which two of the following relate to Earned Value (EV)? (FPM2ed p.337)

a. Earned value outlines how much the project will make when complete.

b. Earned value outlines how much the project has earned to timenow.

c. Earned value outlines how much the project manager has earned.

d. Earned value is a measurement of the work done to timenow.

27.4 Answer: B and D are correct. A and C are incorrect.

27.5: Which two of the following relate to Actual Value (AV)? (FPM2ed p.337)

a. The actual value is the budget to timenow.

b. The actual cost is the cost of performing the work that relates to the work that quantifies the earned value (EV).

c. The actual value is the budget to complete the project.

d. The actual cost is the cost of performing the work to timenow.

27.5 Answer: B and D are correct. A and C are incorrect.

27.6: Which one of the following relates to Estimate at Completion? (FPM2ed p.337)

a. The estimate at completion is the estimate at timenow.

b. The estimate at completion is the estimate at the data date.

c. The estimate at completion is the estimate to complete the total project based on the project’s performance.

d. The estimate at completion is equal to the actual value.

27.6 Answer: C is correct as EAC = (AV/EV)*BAC. A, B and D are incorrect.

27.7: If the PV at Timenow is $500, the EV is $400 and the AV is $600, what is the SV and is the project on time, behind or ahead of planned progress? (FPM2ed p.337)

a. SV = AV–EV = 600-400 = 200, this means the project is ahead.

b. SV = PV-AV = 500-600 = -100, this means the project is behind planned progress.

c. SV = EV-PV = 400-500 = -100, this means the project is behind planned progress.

d. SV = EV-PV = 400-500 = -100, this means the project is ahead.

27.7 Answer: C is correct as SV = EV-PV. A, B and D are incorrect.

27.8: If the PV at Timenow is $500, the EV is $400 and the AV is $600, what is the CV and is the project on budget, under budget or over budget? (FPM2ed p.337)

a. CV = AV-EV = 600-400 = 200, this means the project is under budget.

b. CV = EV-PV = 400-500 = -100, this means the project is over budget.

c. CV = EV-AV = 400-600 = -200, this means the project is over budget.

d. CV = EV+AV = 400+600 = 1,000, this means the project is under budget.

27.8 Answer: C is correct as CV = EV-AV. A, B and D are incorrect.

27.9: If the PV at Timenow is $1,000, the EV is $800 and the AV is $1,200, what is the SPI (Schedule Performance Index)? (FPM2ed p.337)

a. SPI = EV-PV, 800-1,000 = -200, the project is behind planned progress.

b. SPI = AV-PV, 1,200-1,000 = 200, the project is behind planned progress.

c. SPI = EV/AV, 800/1,200 = 0.6, the project is behind planned progress.

d. SPI = EV/PV, 800/1,000 = 0.8, the project is behind planned progress.

27.9 Answer: D is correct as SPI = EV/PV. A, B and C are incorrect.

27.10: If the PV at timenow is $1,000, the EV is $800 and the AV is $1,200, what is the CPI (Cost Performance Index)? (FPM2ed p.337)

a. CPI = EV-AV, 800-1,200 = -400, this means the project is over budget.

b. CPI = EV/AV, 800/1,200 = 0.6, this means the project is over budget.

c. CPI = EV+AV, 800+1,200 = 2,000, this means the project is over budget.

d. CPI = EV-PV, 800-1,000 = -200, this means the project is over budget.

27.10 Answer: B is correct as CPI = EV/AV. A, C and D are incorrect.