## Sheet1
SAQA 58395 | NQF Level 5
US 243811 | Determine the work required to accomplish the objectives and organise the scope of a simple to moderately complex project |  | PMT3ed, Ch 13, Project Scope Management, pages 152-163
US 243812 | Monitor and control the execution of the project management plan for a simple to moderately complex project |  | PMT3ed, Ch 22, Project Control, pages 264-277
US 243813 | Develop a project cost management plan for a simple to moderately complex project |  | PMT3ed, Ch 20, Project Cost Management, pages 234-247
US 243814 | Establish a project or project phase and its processes for a simple to moderately complex project |  | PMT3ed, Ch 12, Project Plan, pages 140-151
US 243815 | Manage stakeholder relations on a project |  | PMT3ed, Ch 27, Project Stakeholder Management, pages 334-343
US 243816 | Develop a project quality management plan for a simple to moderately complex project |  | PMT3ed, Ch 24, Project Quality Management, pages 296-307
US 243817 | Develop a project risk management plan for a simple to moderately complex project |  | PMT3ed, Ch 25, Project Risk Management, pages 308-321
US 243818 | Negotiate agreements in simple to moderately complex situations
US 243819 | Coordinate the closure of a simple to moderately complex project |  | PMT3ed, Ch 10, Project Commissioning and Handover Phase, pages 120-131
US 243820 | Develop an optimised work and resource schedule for a simple to moderately complex project |  | PMT3ed, Ch 19, Project Resource Management, pages 224-233
US 243821 | Manage the procurement process for a simple to moderately complex project |  | PMT3ed, Ch 18, Project Procurement Management, pages 212-223
US 243822 | Manage project communication for a project |  | PMT3ed, Ch 26, Project Communication Management, pages 322-333
US 243823 | Develop a preliminary project scope statement for a simple to moderately complex project |  | PMT3ed, Ch 13, Project Scope Management, pages 152-163
US 243824 | Develop an integrated Project Management plan for a simple to moderately complex project |  | PMT3ed, Ch 12, Project Plan, pages 140-151
US 243825 | Determine project cost and schedule performance using earned value management techniques |  | PMT3ed, Ch 23, Earned Value, pages 278-295
US 243823 | Develop a preliminary project scope statement for a simple to moderately complex project | Range | PMT3ed
Specific Outcome 1: | Interpret the project charter or brief and associated documents |  | PMT3ed, Ch 7, Project Feasibility Phase, pages 88-101
Assessment Criteria | 1.1 Reasons for undertaking the project are interpreted and described to reflect the desired outcomes of project
1.2 Goals and objective of the project are identified and described in line with project charter
1.3 The way the project integrates with the overall business strategy is interpreted and described in line with the project charter
Specific Outcome 2: | Determine the key requirements of the project |  | PMT3ed, Ch 7, Project Feasibility Phase, pages 88-101
Assessment Criteria | 2.1 The products of the project required to achieve the objectives of the project, are identified and described
2.2 The major deliverables required to produce the products of the project, are identified, described and recorded in the required format
2.3 The major resources groupings required to achieve the major deliverables are identified and documented in the required format
2.4 Inclusions and exclusions from the project are identified and documented in the required format in support of project scope clarification agreements
2.5 An initial project schedule is compiled to determine the initial overall timeline of the project and is documented in the required format
2.6 The initial project budget is compiled to determine the feasibility of the project and is documented in the required format
Specific Outcome 3: | Develop the project management approach |  | PMT3ed, Ch 12, Project Plan, pages 140-151
Assessment Criteria | 3.1 The major project assumptions and constraints are identified and documented in the required format
3.2 Major project assumptions and constraints are interpreted and the impact thereof on the project is explained
3.3 Project strategies are identified and described in the context of both its alignment with project objectives and practicality
3.4 Project controls required to govern the project are determined and documented in the required format
3.5 Performance measures and acceptance criteria are identified and explained in support of project objectives
3.6 The project management approach is compiled to best suit the specific project and the stakeholder requirements
Specific Outcome 4: | Compile a preliminary project scope statement |  | PMT3ed, Ch 13, Project Scope Management, pages 152-163
Assessment Criteria | 4.1 All components of the preliminary scope statement are gathered, interrogated and checked for cohesion and balance between them to ensure alignment between them
4.2 Revisions to correct discrepancies between components are agreed with relevant stakeholders and in the required format
4.3 All components are integrated into the preliminary scope statement document in the required format
4.4 The preliminary scope statement document is submitted and presented for approval by the authorised individuals in the required format and time frame
4.5 The approved preliminary scope statement is communicated to all relevant stakeholders in the required format and time frame
US 243812 | Monitor and control the execution of the project management plan for a simple to moderately complex project | Range | PMT3ed
Specific Outcome 1: | Monitor and control the performance of the project |  | PMT3ed, Ch 22, Project Control, pages 264-277
Assessment Criteria | 1.1 Performance is monitored and measured in accordance with project procedures
1.2 Performance results are evaluated against the project management plan in accordance with project procedures
1.3 Preventative and / or corrective actions are developed to ensure compliance to the project management plan
1.4 Opportunities are identified and actions are developed to benefit from such opportunities in support of project objectives
1.5 Developed actions are validated to ensure that it will achieve the desired outcomes
1.6 Developed actions are implemented in accordance with project procedures
1.7 Performance is reported to stakeholders in required format and time frame
Specific Outcome 2: | Manage project baselines through integrated change control |  | PMT3ed, Ch 13, Project Scope Management, pages 152-163
Assessment Criteria | 2.1 Change needs are identified and recorded in accordance with project change control procedures
2.2 The impact of the change needs are assessed and evaluated in terms of the relevant baselines
2.3 Recommendations to address the change needs are compiled in required format and approval obtained in accordance with project change control procedures
2.4 Approved changes are implemented in accordance with project change control procedures
2.5 Change information is communicated to relevant stakeholders in accordance with project change control procedures
Specific Outcome 3: | Manage and resolve issues and new risks |  | PMT3ed, Ch 25, Project Risk Management, pages 308-321
Assessment Criteria | 3.1 Issues are identified and addressed in accordance with project procedures to achieve project objectives
3.2 New risks are identified and addressed in accordance with project procedures to achieve project objectives
3.3 Issues and new risks that may have an change impact on the project, are dealt with in accordance with project change control procedures
| Manage the development of the products of the project |  | PMT3ed, Ch 27, Project Stakeholder Management, pages 334-343
Assessment Criteria | 4.1 Opportunity is provided to clarify product requirements with relevant stakeholders
4.2 Product acceptance criteria are agreed upon and documented in appropriate level of detail
4.3 Proposed product solutions are agreed with relevant stakeholders in appropriate level of detail and in the required time frame
4.4 Product performance evaluations are scheduled and conducted with relevant stakeholders to ensure compliance with product requirements
4.5 Defect resolution and / or change needs are identified and dealt with in accordance with project change control procedures
US 243813 | Develop a project cost management plan for a simple to moderately complex project | Range | PMT3ed
Specific Outcome 1: | Demonstrate an understanding of cost management planning processes and techniques |  | PMT3ed, Ch 20, Project Cost Management, pages 234-247
Assessment Criteria | 1.1 Purpose and content of a cost management plan are described with examples of the benefit derived of having an effective plan
1.2 Processes for producing a project cost management plan are described with examples which are in line with organisational requirements
1.3 Alternative costing methods and models are described with examples of their impact
1.4 Factors affecting project costs are identified and explained with examples of how these factors affect the project costs
1.5 The importance of managing income and expenditure on a project is explained with examples of how this impacts the project outcome
Specific Outcome 2: | Develop cost estimates for a simple to moderately complex project |  | PMT3ed, Ch 20, Project Cost Management, pages 234-247
Assessment Criteria | 2.1 Tools and templates for developing and recording cost estimates are sourced and agreed with relevant parties
2.2 Cost management standards and policies are sourced and adapted for a project in agreement with relevant parties and in accordance with organisational policy
2.3 Project scope, needs and constraints are interpreted and their impact on cost estimates recorded in accordance with organisational procedures
2.4 Resource needs are verified and resource costs are sourced in accordance with agreed procedures
2.5 Cost estimates are developed and recorded in accordance with project needs
2.6 Risks associated with cost estimates are analysed and preventative or recovery action with cost implications are agreed in required format
2.7 Contingency or reserve estimates are developed and recommended in accordance with organisational procedures
Specific Outcome 3: | Develop the project cost baseline |  | PMT3ed, Ch 20, Project Cost Management, pages 234-247
Assessment Criteria | 3.1 Cost estimates are consolidated and figures checked for correctness and accuracy in terms of agreed standards, rules and project needs
3.2 Cost of related groups of activities are aggregated according to agreed needs and structures
3.3 Agreement is obtained on the time-phases to be used for recording expectation of occurrence of funding and or commitments and or income and or expenditure
3.4 Cash flows that reflect control needs of the project and/or organisation are produced in accordance with agreed formats
3.5 Contingency and reserve management needs are estimated and recorded according to required methods
3.6 Budget outputs are consolidated into a cost baseline in accordance with required organisational format and procedure
Specific Outcome 4: | Consolidate information and agree cost management plan |  | PMT3ed, Ch 20, Project Cost Management, pages 234-247
Assessment Criteria | 4.1 Supporting information is consolidated and recorded in agreed formats
4.2 Process and procedures to be used to manage the finances of the project are agreed and recorded in required format
| 4.3 Roles and responsibilities associated with cost management are agreed and recorded in accordance with organisational practices and procedures | (Range: Roles and responsibilities could include but is not limited to: decision making, authorisation, payment processing, recording, performance analysis, budget maintenance)
4.4 Financial data is presented in required format
4.5 Risk contingency and reserve management needs, process and responsibilities are agreed and documented
4.6 Cost management plan is compiled incorporating all components as per agreed procedures
4.7 Cost management plan is agreed by relevant parties following organisational procedure
US 243814 | Establish a project or project phase and its processes for a simple to moderately complex project | Range | PMT3ed
Specific Outcome 1: | Demonstrate an understanding of the project and the project management procedures |  | PMT3ed, Ch 2, Project Life Cycle, pages, 36-49
Assessment Criteria | 1.1 The purpose, approach, scope, deliverables and time frames of the project are explained in accordance with approved project management plan
1.2 Project management processes and phases are identified and explained in line with project management plan and agreed timelines
| 1.3 Project methodology to be used is explained in accordance with the approved project management plan and operating requirements | (Range: Project methodologies include but are not limited to control procedures, purchasing procedures, templates and standards) | PMT3ed, Ch 4, Project Methodology System Approach, pages 56-65
1.4 Stakeholder relationship management and communication management plan and methods are explained in accordance with project management plan
Specific Outcome 2: | Acquire and induct project team members |  | PMT3ed, Ch 29, Project Team, pages 362-371
Assessment Criteria | 2.1 Project team members are identified and acquired in line with defined project roles and responsibilities | (Range: team members may be permanent or contracted)
2.2 Team members are briefed and orientated on the project and work environment within required time frame
2.3 Team and or individual roles and responsibilities are delegated according to project management plan
2.4 Project work is allocated to individual project team members in accordance with the project management plan
2.5 Individual team members needs are identified and addressed in accordance with legislative and/or organisational policy and/or project policy
2.6 Project team rules are discussed and agreed with team members and recorded in required format
Specific Outcome 3: | Acquire and allocate ‘non-people’ resources for the project | (Range: Resources may include but is not limited to: equipment, tools, seating, furniture, communication tools such as web access, e-mail, cell phones, specialised equipment) | PMT3ed, Ch 19, Project Resource Management, pages 224-233
Assessment Criteria | 3.1 Resources are acquired in accordance with agreed project management plan and or internal or external acquisition procedures
3.2 Resources are allocated in accordance with agreed project management plan
3.3 Resources required by team members to conduct project work are available as and when required
3.4 Project asset register is maintained in line with project and or organisational standards and procedures
Specific Outcome 4: | Establish physical and virtual workplace environment | (Range: Virtual workplace may include but is not limited to: project activities are not always conducted in the same physical location) | PMT3ed, Ch 12, Project Plan, pages 140-151
Assessment Criteria | 4.1 Available facilities are investigated and needs to accommodate project team members and other resources are identified in accordance with legislation, project management plan and team member needs | (Range: needs could include but are not limited to: seating, storage, communications, technology, access, equipment, special needs of team members e.g. wheelchair access)
4.2 A safe working environment is established in accordance with relevant legislation
4.3 A secure working environment is established in line with integrated project plan
Specific Outcome 5: | Develop project procedures, standards and templates |  | PMT3ed, Ch 26, Project Communication Management, pages 322-333
Assessment Criteria | 5.1 A team charter is compiled in the required format and describes the expected teams behaviours
| 5.2 Project control procedures are compiled in accordance with project management plan requirements | (Range: Control could include but are not limited to: safety requirements, reporting escalation, change control, purchasing, approvals, levels of authorities)
| 5.3 Documentation procedures and standards are compiled in accordance with project management plan requirements | (Range: standards could include but are not limited to: naming, filing of content)
US 243815 | Manage stakeholder relations on a project | Range | PMT3ed
Specific Outcome 1: | Identify key stakeholders of the project |  | PMT3ed, Ch 27, Project Stakeholder Management, pages 334-343
Assessment Criteria | 1.1 Potential stakeholders are identified and listed in the required format
1.2 The interests that potential stakeholders have in the project is determined and documented in the required format
1.3 The influence that potential stakeholders have on the outcomes of the project is determined and documented in the required format
1.4 Stakeholders are grouped in terms of their interest and influence on the project
1.5 Key stakeholders are identified based on their interest and influence on the project
Specific Outcome 2: | Compile a stakeholder relationship management plan |  | PMT3ed, Ch 27, Project Stakeholder Management, pages 334-343
Assessment Criteria | 2.1 The attitude of key stakeholders is investigated and recorded to reflect whether they are supportive of the project’s objectives or not
2.2 The interaction and communication requirements of key stakeholders are determined and recorded in the required format
2.3 Protocols applicable to the project are identified and documented in accordance with project requirements
2.4 Key stakeholders’ risks are identified, analysed and documented in accordance with project requirements
2.5 Activities to manage stakeholder relations are defined and documented in accordance with organisational standards and procedures
2.6 A stakeholder communication plan is compiled to address the communication requirements of the key stakeholders
2.7 A stakeholder relationship management plan is compiled incorporating the defined activities, protocols, risks and the stakeholder communication plan
Specific Outcome 3: | Implement the stakeholder relationship management plan |  | PMT3ed, Ch 27, Project Stakeholder Management, pages 334-343
Assessment Criteria | 3.1 The stakeholder relationship management plan is communicated to the project management team in a format understood by the team
3.2 Interactions and communication with key stakeholders are conducted in accordance with the stakeholder relationship management plan and recorded in the required format
3.3 Key stakeholders’ interests are considered when making project decisions in accordance with the stakeholder relationship management plan
| 3.4 Issues associated with key stakeholders are addressed to minimise the impact on project success | (Range: Addressed includes: acceptance as is, acceptance with modification, or rejection. An issue may be addressed without being fully resolved)
3.5 The stakeholder relationship management plan is revised to provide for changes to key stakeholders and their requirements
Specific Outcome 4: | Evaluate the effectiveness of key stakeholders’ involvement in the project |  | PMT3ed, Ch 27, Project Stakeholder Management, pages 334-343
Assessment Criteria | 4.1 Information relating to the effectiveness of stakeholder participation and communication is gathered and assembled according to project requirements
4.2 The information gathered is analysed to establish trends in relation to the contribution to project outcomes
4.3 Remedial actions or recommendations for improvement are determined, documented and presented to higher authority for consideration in projects
US 243816 | Develop a project quality management plan for a simple to moderately complex project | Range | PMT3ed
Specific Outcome 1: | Demonstrate an understanding of project quality management principles |  | PMT3ed, Ch 24, Project Quality Management, pages 296-307
Assessment Criteria | 1.1 The purpose of quality management on a project is explained with examples
1.2 The processes required to manage quality on a project are explained, with examples, in accordance with organisational standards and practices or recognised industry practice
1.3 The components of a project quality management plan is explained with examples
1.4 Quality assurance and the application thereof on a project is explained with examples
1.5 Quality control and the application thereof on a project is explained with examples
1.6 Continuous process improvement and the application thereof on a project is explained with examples
1.7 Cost-benefits analyses and the application thereof in quality management is explained with examples
| 1.8 Methods, tools and techniques for analysing and measuring quality needs and performance are described with examples of application to a project | (Range: Methods, tools and techniques may include but is not limited to cause and effect diagrams, Taguchi, Pareto chart or diagram, statistical sampling, trend analysis, Six Sigma, control charts)
Specific Outcome 2: | Gather and analyse quality requirements for a project |  | PMT3ed, Ch 24, Project Quality Management, pages 296-307
Assessment Criteria | 2.1 Participants in defining quality requirements for the project are identified and involved in the project quality planning process
2.2 Project quality objectives are determined with input from the relevant stakeholders and documented in the required format
2.3 Organisational quality policies, procedures and standards are identified and reviewed for applicability
2.4 Established quality management methods, tools and techniques are identified and reviewed for applicability
| 2.5 Requirements for a project quality management system are determined in support of the project quality objectives | (Range: The project quality system may include but is not limited to: organisation structure, responsibilities, procedures, processes, resources, tools, check lists, operational definitions)
2.6 Lessons learned from previous project are identified and reviewed for applicability
2.7 Product quality requirements and criteria are identified with input from the relevant stakeholders and documented in the required format
Specific Outcome 3: | Compile the project quality management plan |  | PMT3ed, Ch 24, Project Quality Management, pages 296-307
Assessment Criteria | 3.1 Quality policies, procedures and standards applicable to the project are selected and documented in the required format
| 3.2 Quality criteria are determined with input from the relevant stakeholders and documented in the required format | (Range: Quality criteria include but are not limited to quality measurements and variances)
3.3 Quality management activities and resource requirements are determined and incorporated in the project schedule
3.4 Roles and responsibilities for quality management activities are defined and agreed with relevant stakeholders
3.5 The budget for quality management activities is determined and agreed with relevant stakeholders
3.6 The project quality management system is defined to meet requirements and agreed with relevant stakeholders
3.7 All project quality management planning components are gathered and consolidated into a project quality management plan in the required format
3.8 The project quality management plan provides for quality assurance, quality control and process improvements
Specific Outcome 4: | Obtain approval for the project quality management plan |  | PMT3ed, Ch 24, Project Quality Management, pages 296-307
Assessment Criteria | 4.1 The project quality management plan is presented to relevant project authorities for approval
4.2 The project quality management plan is incorporated in integrated project management plan
4.3 The project quality management plan is communicated to all relevant stakeholders
US 243817 | Develop a project risk management plan for a simple to moderately complex project | Range | PMT3ed
Specific Outcome 1: | Demonstrate an understanding of the project risk management processes (excludes quantification models) |  | PMT3ed, Ch25, Project Risk Management, pages 308-321
Assessment Criteria | 1.1 The purpose of risk management on a project is explained in line with meeting project objectives
1.2 The relationship of risk management to project planning is explained with examples of their impact on each other
1.3 The development and content of a risk management plan is described in accordance with accepted best project management practice
1.4 Methods of identifying risks are explained with examples in accordance with organisational risk standards and procedures
1.5 Monitoring and controlling of risk and management of issues are explained in accordance with project needs and requirements
Specific Outcome 2: | Identify the risks that apply to a project | (Range: Identify risks may include the facilitation of relevant stakeholders’ knowledge to obtain a list of risks) | PMT3ed, Ch 25, Project Risk Management, pages 308-321
Assessment Criteria | 2.1 Participants who contribute to risk identification and planning are identified in the context of the project scope and procedures
| 2.2 Sources of potential risk are identified in conjunction with other planning activities | (Range: Sources include but are not limited to: enterprise environmental factors, information from prior projects, organisation, participants and other stakeholders)
2.3 Risks associated with the stakeholders of the project are identified and recorded in accordance with agreed formats and procedures
2.4 Risks associated with the products of the project are identified and recorded in accordance with agreed formats and procedures
2.5 Risks associated with the project management processes, resources and deliverables are identified and recorded in required format
Specific Outcome 3: | Analyse the threats and opportunities of a project |  | PMT3ed, Ch 25, Project Risk Management, pages 308-321
Assessment Criteria | 3.1 Causes and effects of threats and/or opportunities are determined and recorded in accordance with agreed procedures
3.2 A risk register is created and maintained for the project in accordance with agreed procedures
3.3 Risk owners are identified and documented in accordance with agreement procedures
| 3.4 Levels of likelihood (probability) and impact of risk events are assessed and recorded in consultation with experts | (Range: Experts include but are not limited to internal and external stakeholders, subject matter experts, consultants)
3.5 Timing of risk occurrence is defined and documented in accordance with agreed procedures
3.6 Risks are categorised and prioritised in terms of impact on the project in accordance with agreed procedures
3.7 Impacts of the risks on project objectives are analysed, agreed and documented in accordance with agreed procedures
Specific Outcome 4: | Develop responses for risks and compile a risk management plan |  | PMT3ed, Ch 25, Project Risk Management, pages 308-321
Assessment Criteria | 3.1 Strategies are developed for responding to the risks in accordance with standard organisational practices | (Range: Strategies could include but are not limited to: avoid, transfer, mitigate, accept, exploit, share, enhance, contingent response strategy)
3.2 Risk recovery and prevention activities are defined and costed in required format
3.3 Contingency requirements and approach are developed and agreed in required format
3.4 Processes, procedures and responsibilities for managing risks are agreed and developed according to policy and procedure
3.5 Risk management activities are assigned to team members and risk owners documented in accordance with agreed responsibilities and procedures
US 243818 | Negotiate agreements in simple to moderately complex situations | Range | PMT3ed
Specific Outcome 1: | Demonstrate an understanding of negotiation concepts |  | PMT3ed, Ch 12, Project Plan, pages 140-151
Assessment Criteria | 1.1 Situations that require negotiation skills are described with examples |  | PMT3ed, Ch 5, Request for Proposal, pages 66-77
1.2 Alternative process models for negotiation are compared using examples
1.3 Types of negotiation are identified and described with examples of their application in your sector
| 1.4 Negotiation styles are identified and listed with examples | (Range = Styles would include but are not limited to: forcing/adversarial, accommodating, compromising, collaborative / non-adversarial)
1.5 Factors that influence negotiation are described with examples as they occur in your business environment
1.6 Key characteristics of a successful negotiator are described with examples
Specific Outcome 2: | Develop a strategy to achieve successful negotiations |  | PMT3ed, Ch 12, Project Plan, pages 140-151
Assessment Criteria | 2.1
| 2.2 Potential stakeholders in the negotiation are identified and profiled in accordance with their position to negotiation subject | (Range: Profile may include but is not limited to attitude, involvement, benefit, role, authority) | PMT3ed, Ch 27, Project Stakeholder Management, pages 334-343
| 2.3 Alternative negotiation strategy and structures are identified and one is selected in accordance with needs and best fit for its purpose | (Range: The negotiation strategies include at least three contemporary strategies such as distributive, integrated, principled, interest-based and target-specific bargaining)
Specific Outcome 3: | Conduct negotiations |  | PMT3ed, Ch 6, Corporate Strategy Phases, pages 78-87
Assessment Criteria | 3.1 Negotiations are prepared for in accordance with business needs and in line with organisational procedures | (Range: preparation may include but is not limited to any of identifying and informing stakeholders and / or participants; obtaining agreement on position to negotiate from constituency, information gathered, logistical arrangements made)
3.2 Behaviour and conduct during negotiations are aligned with the selected negotiation strategy and tactics
3.3 Negotiations are conducted within the mandate received and in line with organisational standards and procedures
3.4 Negotiated outcomes are clearly presented, explained and motivated to stakeholders and constituency
3.5 Appropriate action is initiated to obtain an amended mandate if required in accordance with organisational standards and procedures
3.6 Proceedings and interim outcomes are recorded in the required format for feedback purposes
Specific Outcome 4: | Identify and overcome difficulties and conflict during negotiations |  | PMT3ed, Ch 28, Project Leadership and Entrepreneurship, pages 344-361
Assessment Criteria | 4.1 Potential issues or areas for conflict are identified, recorded and notified in terms that they allow timely resolution
4.2 Symptoms of conflict are identified and root causes determined using recognised techniques
4.3 Appropriate conflict resolution methods and techniques are identified, selected and applied to solve the problem
Specific Outcome 5: | Finalise and communicate the agreement |  | PMT3ed, Ch 26, Project Communication Management, pages 322-333
Assessment Criteria | 5.1 Negotiated agreements are recorded in required format using industry terminology and in accordance with organisational standards and procedures.
5.2 The final written agreement is distributed within the required time frame and format and is explained to all constituents and stakeholders.
US 243819 | Coordinate the closure of a simple to moderately complex project | Range | PMT3ed
Specific Outcome 1: | Verify and validate that the products of the project are ready for handover | (Range: This includes checking that work done by others is complete. Checking that the product includes final end product and any related deliverables that must be handed over into operational use at project termination / closure) | PMT3ed, Ch 13, Project Scope Management, pages 152-163
Assessment Criteria | 1.1 All product compliance tests are checked for completion in accordance with project requirements | (Range: compliance tests may include inspections, field tests and any action needed to check that the product meets specification and acceptance criteria)
1.2 All product related documentation are completed in accordance with project requirements and / or contracts
1.3 Non-compliance issues are analysed and resolved to the satisfaction of all relevant parties, and documents are ready for handover to the client or to operation status
Specific Outcome 2: | Hand over the products of the project |  | PMT3ed, Ch 10, Project Commissioning and Handover Phase, pages 120-131
Assessment Criteria | 2.1 The products of the project are handed over to authorised individual in accordance with organisational practises and project agreements
2.2 Signed product acceptance certificates are obtained using agreed formats and procedures
2.3 All handovers and related documents are logged and the records incorporated in project files
Specific Outcome 3: | Close project administration, client agreements and release project resources |  | PMT3ed, Ch 10, Project Commissioning and Handover Phase, pages 120-131
Assessment Criteria | 3.1 Project closure activities are scheduled in accordance with project management plan
3.2 Project records are finalised, signed off and stored in compliance with policies and procedures
3.3 Project resources are released within required time frame and in accordance with project management plan
3.4 Client agreements are closed in accordance with contractual and/or project requirements
Specific Outcome 4: | Participate in conducting the project performance review |  | PMT3ed, Ch 10, Project Commissioning and Handover Phase, pages 120-131
Assessment Criteria | 4.1 Client and stakeholder management strategies are evaluated for effectiveness against project objectives and findings are recorded for review purposes
4.2 Effectiveness of the project management approach is evaluated against project objectives and findings are recorded for review purposes
4.3 Change to policies, procedures, and standards are recommended in required format
4.4 Improvement areas are identified and reported on in required format and time frame
4.5 Lessons learned are developed, documented and reported according to project requirements
Specific Outcome 5: | Communicate project closure to all stakeholders |  | PMT3ed, Ch 27, Project Stakeholder Management, pages 334-343
Assessment Criteria | 5.1 Project closure is communicated to all stakeholders in accordance with the project communication plan
5.2 Results of the project review are communicated to all stakeholders in required format and time frame
5.3 Knowledge bases are updated in required format and made available in required format for future use
5.4 Details of incomplete deliverables or potential product modifications are communicated to the group charged with future support of the final product in its operational life in the required format
US 243820 | Develop an optimised work and resource schedule for a simple to moderately complex project | Range | PMT3ed
Specific Outcome 1: | Demonstrate an understanding of scheduling tools and techniques |  | PMT3ed, Ch 16, Critical path Management (CPM), pages 186-199
Assessment Criteria | 1.1 Purpose of using schedules on a project is explained with examples of the benefits derived |  | PMT3ed, Ch 17, Gantt Charts, pages 200-211
| 1.2 The process and techniques for developing a schedule are explained with examples appropriate to project type and or project management needs |  | PMT3ed, Ch 15, Project Schedule Management, pages 176-185
| 1.3 Usage of alternative start and finish dates on a schedule is explained with examples of their impact | (Range: may include but are not limited to early/late, fixed dates)
| 1.4 The process and techniques for resource planning are explained with examples appropriate to project type and or project management needs | (Range: may include but is not limited to resource identification, allocation, loading and levelling)
| 1.5 The process and techniques to optimise project schedules in order to complete the work within project constraints, are explained with examples appropriate to project type and or project management needs | (Range: Project constraints may include but are not limited to time, resources, nature of the activity/deliverable, cash flow)
1.6 Different ways of representing a project schedule is explained with examples of appropriate use
Specific Outcome 2: | Produce an initial work schedule |  | PMT3ed, Ch 17, Gantt Charts, pages 200-211
Assessment Criteria | 2.1 Activities are identified and described in terms of the work required to address the scope of the project
2.2 Dependencies between activities are defined and activities are sequenced to reflect the logic relationship of the work
2.3 Durations of activities are estimated, in consultation with experts, and / or in accordance with procedures
2.4 Time based work schedules are produced in accordance with procedures and in required format
2.5 Initial critical path is identified and explained in accordance with standard organisational procedures
Specific Outcome 3: | Identify and estimate resources for each activity |  | PMT3ed, Ch 15, Project Schedule Management, pages 176-185
Assessment Criteria | 3.1 Resource requirements are defined by activity in accordance with agreed procedures and or standards |  | PMT3ed, Ch 19, Project Resource Management, pages 224-233
3.2 Quantities of resources are defined per activity as per initial work schedule and in accordance with established procedures and or standards
3.3 Resource availability and costs are researched and compared using agreed procedures and or standards
| 3.4 Resource plan is developed and agreed with relevant stakeholder in accordance with procedures and in required format | (Range: Resource plan may include but is not limited to resource category and/or types, quantities, availability, capability, resource calendars, activity resource requirements, resource risk analysis and management actions)
Specific Outcome 4: | Optimise the work and resource schedule |  | PMT3ed, Ch 19, Project Resource Management, pages 224-233
Assessment Criteria | 4.1 Resources are allocated to activities on the schedule according to resource plan, their availability, standards and procedures
| 4.2 Potential resource constraints, conflict, under or over utilisation situations are identified and explained in terms of their impact on the project work |  | PMT3ed, Ch 28, Project Leadership and Entrepreneurship, pages 344-361
4.3 Risk analysis of work and resources is undertaken and documented according to agreed procedures
4.4 Resource usage and work/activity timing is adjusted to produce a realistic schedule
| 4.5 Optimised work and resource schedule is agreed with responsible parties in accordance with agreed procedures | (Range: realistic schedule recognises project and work constraints and allocates resources for agreed and acceptable time frames)
Specific Outcome 5: | Compile the schedule and resource management plans |  | PMT3ed, Ch 19, Project Resource Management, pages 224-233
Assessment Criteria | 5.1 Work and resource schedule is base lined in accordance with standards and procedures
5.2 Schedule management plan is produced incorporating agreements in accordance with procedures and standards
5.3 Resource management plan is produced incorporating agreements in accordance with procedures and standards
US 243821 | Manage the procurement process for a simple to moderately complex project | Range | PMT3ed
Specific Outcome 1: | Demonstrate an understanding of project procurement management principles |  | PMT3ed, Ch 18, Project Procurement Management, pages 212-223
Assessment Criteria | 1.1 Organisational procurement policies and procedures applicable to the project environment are explained |  | PMT3ed, Ch 5, Request for Proposal, pages 66-77
1.2 Contract types and the application thereof are explained for different resource categories and project conditions
1.3 Procurement lead times and the impact thereof on the project schedule are explained
1.4 Knowledge of the supplier market is demonstrated for three resource categories, including estimated procurement lead times for these resource categories
1.5 Contract administration procedures applicable to the project are explained
Specific Outcome 2: | Compile the procurement management plan in support of the project plan |  | PMT3ed, Ch 18, Project Procurement Management, pages 212-223
Assessment Criteria | 2.1 Goods and services that need to be sourced from outside the project organisation are identified and categorised in procurement groups
2.2 Sourcing requirements are determined for each procurement group
2.3 Potential sources of supply are identified to supply goods and services in accordance with sourcing requirements and relevant procurement policies and procedures
2.4 Lead times are determined for the supply of goods and services based on knowledge of the market or a market analysis
2.5 Sourcing activities are scheduled in support of the project plan and provide for sourcing lead times
2.6 Responsibilities are allocated to sourcing activities in accordance with the roles and responsibility matrix of the project
2.7 The procurement management plan is compile from the above information and submitted for approval by the relevant authority
Specific Outcome 3: | Request responses from qualified suppliers in accordance with the procurement management plan |  | PMT3ed, Ch 5, Request for Proposal, pages 66-77
Assessment Criteria | 3.1 A contract statement of work is compiled in accordance with the project requirements for each contract
3.2 Bid documents are compiled in accordance with organisational procurement policies and procedures and reflect the contract statement of work and other relevant project requirements
3.3 A list of qualified suppliers is compiled in accordance with organisational procurement policies an procedures and reflects the required information of each supplier
3.4 Bid documents are issued to qualified suppliers in accordance with the procurement management plan and organisational procurement policies and procedures
Specific Outcome 4: | Evaluate responses received and select the supplier to supply the relevant goods or services to the project |  | PMT3ed, Ch 5, Request for Proposal, pages 66-77
Assessment Criteria | 4.1 Evaluation criteria to asses responses are compiled in accordance with project requirements and organisational procurement policies and procedures
4.2 Responses are evaluated in accordance with the relevant evaluation criteria and the preferred supplier is identified
4.3 A recommendation is compiled and submitted to the relevant adjudication authority to select the successful supplier
4.4 Realistic cost and time values to be used for the project baseline are established in the required format based on the responses evaluated
Specific Outcome 5: | Establish agreements with successful suppliers and acquire goods or services for the project |  | PMT3ed, Ch 18, Project Procurement Management, pages 212-223
Assessment Criteria | 5.1 Supply agreements are compiled in accordance with the responses received, the mandate received from the adjudication authority and the organisational procurement policies and procedures to provide for specific project requirements |  | PMT3ed, Ch 5, Request for Proposal, pages 66-77
5.2 Agreement requirements, terms and conditions, schedules and prices are clarified and negotiated with successful suppliers in accordance with relevant procedures
5.3 Agreements for the supply of goods and services are established with successful suppliers in accordance with relevant procedures
5.4 Goods and services are acquired from suppliers in accordance with project requirements and established supply agreements
Specific Outcome 6: | Administer the supplier agreements |  | PMT3ed, Ch 18, Project Procurement Management, pages 212-223
Assessment Criteria | 6.1 The performance of suppliers are monitored and measured against the agreement |  | PMT3ed, Ch 5, Request for Proposal, pages 66-77
6.2 Contract payments are administered in accordance with performance, contractual agreements and organisational policies and procedures
6.3 Issues and risks are identified and addressed within delegated authority, and escalated to the appropriate level of authority if it is outside own level of authority
6.4 Change requests are processed and addressed in accordance with project and contractual requirements
6.5 Contract close-out is under taken in accordance with project requirements and agreed procedures
US 243822 | Manage project communication for a project | Range | PMT3ed
Specific Outcome 1: | Demonstrate an understanding of the characteristics of communication |  | PMT3ed, Ch 26, Project Communication Management, pages 322-333
Assessment Criteria | 1.1 The importance of effective communication on a project is explained with examples
| 1.2 The basics of a communication model are described with examples of the application thereof on a project | (Range: Basic communication model may include but is not limited to source, encoding, media, channel, decoding, sender, receiver, response, feedback, noise, listening)
| 1.3 Potential barriers or levers for successful communication between your project team and your stakeholders are identify and described with examples | (Range; Barriers may include but is not limited to; age, attitude, gender, cultural diversity, ego, etiquette, perception, language, status, health, psychological state, misunderstandings, concentration level, distractions, knowledge and education, interests, needs, personality, use of language including jargon, slang and grammar, prejudices, thoughts and feelings, moods, attention span, environmental factors, technology, blurred messages
Levers – use of home language, recognition of recipient’s cultural expectations, simple uncluttered language)
| 1.4 Types of communication are described with examples of their application in the sector relevant to the project | (Range: Types of communication may include but are not limited to oral communication (including voice, tone, timing and word), written, body language, attire, accessories, facial expressions, body movements, personal space, touch, formal, informal)
| 1.5 Factors that influence communication are described with examples | (Range: Factors may include but not limited to; needs and objectives of respective parties, attitudes and motivations of involved parties, interpersonal skills, emotions, cultural differences confused messages, disruption, effective listening, effective writing, effective speaking, correctness of information, Fog factor)
| 1.6 Methods of communication on a project are described with examples from a project | (Range – letters, reports, email, meetings, press adverts or releases, pictures, tables, charts, graphs, brochures, flyers, theatre, forms, orders, contracts)
Specific Outcome 2: | Develop a communication plan for a project |  | PMT3ed, Ch 26, Project Communication Management, pages 322-333
Assessment Criteria | 2.1 Communication needs are identified in accordance with scope of the project, project constraints and assumptions and the needs of project stakeholders | (Range: Communication needs may include but not limited to content, technology availability and technology competence of sender or recipient, geographic location to project team, role in project, culture, protocol, formal structures, organisation processes, contractual, environmental factors)
2.2 Information needs are analysed, summarised and prioritised using the communication needs and the contribution or value of the information transfer to the project success
2.3 Available communication technologies are researched and viable alternatives proposed in accordance with project environment and constraints
2.4 Potential communication risks are identified and mitigation actions considered to address these risks
2.5 Communication strategy and tactics are developed and agreed in accordance with identified needs, potential risks, available technologies and project constraints or opportunities
2.6 Communications management plan is developed in accordance with agreed strategy and tactics and communications needs
2.7 Communications management plan is agreed and incorporated into overall project management plan
Specific Outcome 3: | Implement a project communication plan |  | PMT3ed, Ch 26, Project Communication Management, pages 322-333
Assessment Criteria | 3.1 A project management information system is implemented to collect, disseminate and record project information in accordance with the communications management plan
3.2 Templates and procedures to support implementation of the communications management plan are developed in accordance with project and / or organisation standards
3.3 Project team members are briefed on procedures and provided with necessary project communication templates and data
| 3.4 Documentation and / or object management is implemented for a project in accordance with organisation or project standards | (Range: Object may include but is not limited to video, audio tapes, theatre props)
3.5 Information is distributed in accordance with project communication management plan
3.6 Performance reports are prepared and distributed in accordance with communications management plan
Specific Outcome 4: | Evaluate the effectiveness of a project communications and implement improvement |  | PMT3ed, Ch 26, Project Communication Management, pages 322-333
Assessment Criteria | 4.1 Risks and / or issues are identified, recorded, analysed and responded to in accordance with project procedures
4.2 Effectiveness of project communication is evaluated and reported on in accordance with project objectives, success criteria and project management plan
4.3 Meeting effectiveness is evaluated and improvements identified and implemented in accordance with project procedures
4.4 Improvements to communications are identified and implemented in accordance with needs and results of evaluation
US 243823 | Develop a preliminary project scope statement for a simple to moderately complex project | Range | PMT3ed
Specific Outcome 1: | Interpret the project charter or brief and associated documents |  | PMT3ed, Ch 7, Project Feasibility Phase, pages 88-101
Assessment Criteria | 1.1 Reasons for undertaking the project are interpreted and described to reflect the desired outcomes of project
1.2 Goals and objective of the project are identified and described in line with project charter
1.3 The way the project integrates with the overall business strategy is interpreted and described in line with the project charter
Specific Outcome 2: | Determine the key requirements of the project |  | PMT3ed, Ch 7, Project Feasibility Phase, pages 88-101
Assessment Criteria | 2.1 The products of the project required to achieve the objectives of the project, are identified and described
| 2.2 The major deliverables required to produce the products of the project, are identified, described and recorded in the required format |  | PMT3ed, Ch 6, Corporate Strategy Phases, pages 78-87
| 2.3 The major resources groupings required to achieve the major deliverables are identified and documented in the required format | (Range: Major resource groupings include but are not limited to project team members, contracting groups, equipment and material)
2.4 Inclusions and exclusions from the project are identified and documented in the required format in support of project scope clarification agreements
| 2.5 An initial project schedule is compiled to determine the initial overall timeline of the project and is documented in the required format | (Range: Initial project schedule consists of key project milestones e.g. key milestone chart)
| 2.6 The initial project budget is compiled to determine the feasibility of the project and is documented in the required format | (Range: Initial project budget is mostly a top-down approach rather that a bottom-up approach when a detailed project budget is compiled)
Specific Outcome 3: | Develop the project management approach |  | PMT3ed, Ch 4, Project Methodology Systems Approach, pages 56-65
Assessment Criteria | 3.1 The major project assumptions and constraints are identified and documented in the required format
3.2 Major project assumptions and constraints are interpreted and the impact thereof on the project is explained
| 3.3 Project strategies are identified and described in the context of both its alignment with project objectives and practicality | (Range: Project strategies include but are not limited to management strategies for scope, schedule, cost, quality, risk, communication)
| 3.4 Project controls required to govern the project are determined and documented in the required format | (Range: Project controls include but are not limited to policies, procedures, standards and guidelines required to govern the project)
3.5 Performance measures and acceptance criteria are identified and explained in support of project objectives
| 3.6 The project management approach is compiled to best suit the specific project and the stakeholder requirements | (Range: The project management approach includes but is not limited to project phases, project management processes and specific strategies regarding key project aspects)
Specific Outcome 4: | Compile a preliminary project scope statement |  | PMT3ed, Ch 13, Project Scope Management, pages 152-163
Assessment Criteria | 4.1 All components of the preliminary scope statement are gathered, interrogated and checked for cohesion and balance between them to ensure alignment between them | (Range: Components include but are not limited to the products of the project, major deliverables, inclusions and exclusions, initial project schedule and budget, assumptions, project strategies, controls and performance measures)
4.2 Revisions to correct discrepancies between components are agreed with relevant stakeholders and in the required format
4.3 All components are integrated into the preliminary scope statement document in the required format
4.4 The preliminary scope statement document is submitted and presented for approval by the authorised individuals in the required format and time frame
4.5 The approved preliminary scope statement is communicated to all relevant stakeholders in the required format and time frame
US 243824 | Develop an integrated Project Management plan for a simple to moderately complex project | Range | PMT3ed
Specific Outcome 1: | Refine the project organisational structure, profiles, roles and responsibilities |  | PMT3ed, Ch 30, Project Organization Structures, pages 372-381
Assessment Criteria | 1.1 Project organisation structure, roles, responsibilities and authorities are refined in consultation with the client and/or management | (Range: may include but is not limited to: project sponsor, project owner, steering committees, reference groups, teams, contractors, specialised roles)
1.2 Project team profiles and structure are refined and documented in line with organisational standards and procedures
1.3 Procedures to refer issues and / or decisions to higher levels of authority, are refined and documented in line with organisational practices and procedures
Specific Outcome 2 | Determine the integrated change control procedures |  | PMT3ed, Ch 13, Project Scope Management, pages 152-163
Assessment Criteria | 2.1 Change request, monitor and control procedures are set up in accordance with organisational and/or client standards and procedures and project needs
2.2 Change control approval procedures and responsibilities are defined in required format
2.3 Configuration control procedures are defined in line with project objectives, product needs and organisational standards and procedures
Specific Outcome 3: | Produce the integrate project management plan document |  | PMT3ed, Ch 12, Project Plan, pages 140-151
Assessment Criteria | 3.1 All component elements and / or plans are gathered, checked and interrogated for cohesion and balance between them to ensure alignment to each other | (Range: component elements may include but are not limited to: scope management plan, schedule, resource management plan, cost management plan, risk management plan, quality management plan, communication management plan, stakeholder management plan, control procedures, baselines)
3.2 Revisions to correct discrepancies between components are agreed with relevant stakeholders and in the required format
3.3 Project control mechanism and processes are defined in accordance with project needs
3.4 Performance measurement baselines are developed and agreed in accordance with agreed success criteria and planned controls
3.5 All components are integrated into the project management plan document
3.6 The project management plan document is checked for accuracy, completeness and compliance to required format
Specific Outcome 4: | Obtain approval for the integrated project management plan |  | PMT3ed, Ch 12, Project Plan, pages 140-151
Assessment Criteria | 4.1 The integrated project management plan is presented to the authorised individuals in required format and time frame |  | PMT3ed. Ch 4, Project Methodology Systems Approach, pages 56-65
4.2 Approval is obtained for the integrated project management plan from the authorised individuals in accordance with organisational standards and procedures
4.3 The approved integrated project management plan is communicated to all stakeholders in the required format and time frame
US 243825 | Determine project cost and schedule performance using earned value management techniques | Range | PMT3ed
Specific Outcome 1: | Decompose project scope into work/planning packages |  | PMT3ed, Ch 14, Work Breakdown Structure (WBS), pages 164-175
Assessment Criteria | 1.1 The total scope of the project is decomposed into work packages (or planning packages for future work) using the work breakdown structure technique or any other approved method. | (Range: Work packages may include planning packages for future work)
1.2 Authorised work and related resources are defined in required format and meet the requirements of the project.
1.3 Internal organisational elements and the major contractors/subcontractors responsible for accomplishing the authorised work are identified and recorded in line with the requirements of the project.
1.4 The planning, scheduling, budgeting, work authorisation and cost accumulation systems are integrated and provide for the organisational and work breakdown structure.
1.5 The individuals responsible for planning, measuring and controlling performance are identified and recorded in required format.
Specific Outcome 2: | Plan and schedule the project scope on a master project schedule |  | PMT3ed, Ch 13, Project Scope Management, pages 152-163
Assessment Criteria | 2.1 Authorised work is scheduled in a manner that describes the sequence of work and identifies the significant task interdependencies required to meet the development, production and delivery requirements of the project. |  | PMT3ed, Ch 14, Work Breakdown Structure (WBS), pages 164-175
2.2 Physical products, deliverables, milestones, technical performance goals, or other indicators that will be used to measure output are identified and integrated with the master schedule.
2.3 Budgets are established for all authorised work in the required format and include where necessary identification of (labour, material, equipment) cost elements.
2.4 A time-phased budgeted cost of work scheduled (planned value) baseline at the cost account level is established against which project performance can be measured.
2.5 Time-phased budgets for level-of-effort work are identified and established in required format for control purposes.
Specific Outcome 3: | Set up and assign cost account plans |  | PMT3ed, Ch 20, Project Cost Management, pages 234-247
Assessment Criteria | 3.1 The sum of all work package budgets, plus planning package budgets within the cost account, equals the cost account plan’s total budget.
3.2 Overhead budgets for the cost of doing business of each organisational component whose expenses will become indirect costs to the project (if not incorporated into the line item rates) are established and reflect in the project budgets at the required level.
3.3 Management reserve (contingency budget) is excluded from the performance measurement baseline.
3.4 Authorised individuals are provided with access to as well as being allowed to input and change, the information and supporting documentation necessary in compliance organisational procedures.
Specific Outcome 4: | Establish and maintain a performance measurement baseline |  | PMT3ed, Ch 22, Project Control, pages 264-277
Assessment Criteria | 4.1 Approved scope changes are incorporated into the performance measurement baseline, recording the effects of such changes in budgets and schedules within the required time frame.
4.2 Original budgets for those elements at the lowest level in the work breakdown structure, to be reconciled with current performance measurement budgets in terms of changes to the authorised work and internal re-planning in the detail needed by management for effective control.
| 4.3 Integrity of records are maintained throughout the project in accordance with project standards | (Range: Records pertaining to work performed that would change previously reported amounts for direct costs, indirect costs, or budgets, except for correction of errors and routine accounting adjustments.)
4.4 Changes to the performance measurement baseline are documented in required format and the procuring activity notified through prescribed organisational procedures.
Specific Outcome 5: | Monitor and control project performance and forecast final cost and schedule outcomes |  | PMT3ed, Ch 22, Project Control, pages 264-277
Assessment Criteria | 5.1 Measurement of task progress and actual costs expended are done at intervals as prescribed by organisational guideline. |  | PMT3ed, Ch 23, Earned Value, pages 278-295
5.2 Direct and indirect costs are measured and recorded on an applied or other acceptable basis in a manner consistent with the budgets in a formal system that is controlled by the general books of account.
5.3 Costs from cost accounts are summarised into the work breakdown structure avoiding allocation of a single cost account to two or more work breakdown structure elements.
5.4 Variances or indexes are noted, resulting from the comparisons between the budgeted cost of work performed (earned value) and the budgeted cost of work scheduled (planed value) and between the budgeted cost of work performed and actual cost of work performed (actual cost), together with the reasons for significant variances.
5.5 Corrective action is taken, in collaboration with higher authority to mitigate negative deviations from the plan.
5.6 Forecasts are made based on cumulative performance indexes to date, to predict and prepare for cost and schedule outcomes at project completion.